## PP
ID | Workstream | Task / Deliverable | Owner (Role) | Start | Start | Finish | Finish | Duration (days) | Status | Dependencies | Notes | Milestone (Y/N)
1 | Design | Game Concept and Game Design Doc | Carlos (Game Designer) | 09/01/2025 | 2025-09-01 | 09/15/2025 | 2025-09-15 | 14 | Completed |  | Scope doc v1 | N
2 | Art | Define visual style (pixel art) | Ana (Art Director) | 09/05/2025 | 2025-09-05 | 09/20/2025 | 2025-09-20 | 15 | Completed |  | Visual reference established | N
3 | Programming | Prototype combat and puzzle mechanics | Luis (Lead Programmer) | 09/15/2025 | 2025-09-15 | 09/30/2025 | 2025-09-30 | 15 | Completed | 1, 2 | Greybox scene | N
4 | Narrative | Level 1 design and Chapter 1 narrative | Marta (Level/Narrative Designer) | 09/20/2025 | 2025-09-20 | 10/05/2025 | 2025-10-05 | 15 | Completed | 1 | Daily stand-up M–F | N
5 | Production | Vertical Slice (fully playable Level 1) | Pedro (Producer) | 10/01/2025 | 2025-10-01 | 10/25/2025 | 2025-10-25 | 24 | In Progress | 3, 4 | Gameplay and art validation | Y
6 | Audio | Audio and music integration | Elena (Audio Designer) | 10/15/2025 | 2025-10-15 | 10/30/2025 | 2025-10-30 | 15 | In Progress | 5 | Basic SFX implemented | N
7 | Programming | Internal gameplay testing (Level 1) | José (QA Lead) | 10/26/2025 | 2025-10-26 | 10/31/2025 | 2025-10-31 | 5 | Not Started | 5 | Full Level 1 playthrough | N
8 | Programming | Iteration and improvements from feedback | Carlos (Game Designer) | 11/01/2025 | 2025-11-01 | 11/15/2025 | 2025-11-15 | 14 | Not Started | 7 | Adjustments based on internal tests | N
9 | Programming | Development of Levels 2–3 (extra content) | Marta (Level Designer) | 11/01/2025 | 2025-11-01 | 12/15/2025 | 2025-12-15 | 44 | Not Started | 5 | Narrative pillars already defined | N
10 | Production | Beta Version (Feature Complete) | Pedro (Producer) | 12/20/2025 | 2025-12-20 | 12/20/2025 | 2025-12-20 | 0 | Not Started | 8, 9 | All gameplay features implemented | Y
11 | Programming | Optimization and handheld console port | Luis (Lead Programmer) | 01/01/2026 | 2026-01-01 | 01/20/2026 | 2026-01-20 | 19 | Not Started | 10 | Targeting 60fps on handheld console | N
12 | Production | Launch (PC Steam & Handheld Console) | Pedro (Producer) | 01/30/2026 | 2026-01-30 | 01/30/2026 | 2026-01-30 | 0 | Not Started | 11 | Final builds to be submitted | N
Formulas:
Duration (days) = DAYS([Finish],[Start])

## Notes
Key Highlights
→ The project is structured around three main phases: Pre-production (Concept, Prototype, Vertical Slice), Production (full content development), and Launch.
→ Vertical Slice is the first major milestone, intended to validate gameplay, visual style, and the full production pipeline.
→ A clear and realistic scope is defined early (Game Design Doc complete by mid-September) to prevent scope creep, a common risk in indie projects.
→ Cross-functional collaboration is emphasized: Level design, combat, and narrative tasks are closely scheduled to support early playability.
→ Dependencies between tasks are carefully defined to ensure smooth progression (e.g., Level 1 design depends on GDD, Vertical Slice depends on combat and narrative).
→ Risks such as performance issues on handheld consoles and timeline slips are mitigated through early prototyping, playtesting, and internal reviews.
→ Each task includes an owner responsible for delivery, aligning with good practices in risk accountability and agile-style progress tracking.
→ Two key milestones are defined: the Vertical Slice (October) and the Feature Complete Beta (December), both used to focus team efforts on tangible deliverables.
→ Creative risks (e.g., narrative or combat not resonating) are addressed by frequent internal testing and iteration phases built into the schedule.
→ Audio and SFX integration is aligned with the Vertical Slice to ensure that the build represents final game atmosphere.
→ Launch is scheduled one month after Beta to allow time for polish, bug fixing, and platform submission processes.