## CL
ID | Requestor | Change Description | Reason / Benefit | Impact on Scope | Impact on Schedule (days) | Impact on Budget | Decision | Decision Date | Owner | Notes | Linked Task ID | Related Risk ID | Related Bug ID
201 | Design | Add enemy variant in vertical slice | Increase combat variety | +1 enemy variant | 3 | None | Deferred | 2025-10-30 | Producer | Review after Level 1 slice | 5 | Risk #1 | —
202 | QA | Fix level 1 softlock puzzle interaction | Critical for milestone play | Puzzle script update | 2 | None | Approved | 2025-10-30 | QA Lead | Reported in Bug ID 103, to unblock milestone | 7 | — | Bug #103
203 | Audio | Polish loop timing in BGM track | Audio quality improvement | BGM file iteration | 0 | None | Approved | 2025-10-29 | Audio Designer | Related to Bug #104 | 6 | — | Bug #104
204 | Producer | Postpone console optimization | Avoid burnout, match capacity | Delay console build | 3 | None | Approved | 2025-10-31 | Producer | Due to performance risk + bug; reprioritized | 11 | Risk #3 | Bug #105

## Notes
Key Highlights
→ This log tracks approved, deferred, or rejected changes during the production cycle.
→ Each change is evaluated for:
▪ Scope impact (new features, modifications)
▪ Schedule impact (added time to complete)
▪ Budget impact (only included if relevant)
→ Changes may be triggered by:
▪ Internal requests (design, QA, production)
▪ Bugs logged in the Issue Triage Sheet
▪ Risk mitigation strategies from the Risk Register
→ Fields:
▪ Linked Task ID refers to the relevant task from the Project Plan (WBS)
▪ Related Risk ID connects to risk mitigation entries
▪ Related Bug ID indicates if change is a response to a logged issue
→ Decisions are made by the Producer and stakeholders during weekly syncs