## BTS
ID | Title | Severity (Blocker/Critical/Major/Minor) | Priority (P1-P4) | Owner | Opened | Target Fix | Status | Description / Repro | Environment | SLA (days) | Notes | Linked Task ID | Related Risk
101 | Crash on load | Blocker | P1 | Engineer | 2025-10-28 | 2025-10-29 | Open | Game crashes immediately after boot | PC build 0.1 | 1 | Escalated to dev lead | 7 | Risk #2
102 | UI overlap in HUD | Minor | P3 | UI/UX | 2025-10-27 | 2025-11-02 | Open | Text overlaps at 1080p resolution | PC build 0.1 | 5 | To be fixed after playtest feedback | 8
103 | Puzzle softlock in level 1 | Critical | P1 | QA Lead | 2025-10-30 | 2025-11-03 | Open | Player can't reset puzzle when stuck | Console dev kit | 3 | Affects milestone playability | 7 | Risk #4
104 | Music loop cuts early | Minor | P4 | Audio Designer | 2025-10-25 | 2025-11-05 | In Progress | BGM track stops abruptly after 60s | PC build 0.1 | 7 | Audio polishing task | 6
105 | Performance drop in fight | Major | P2 | Lead Programmer | 2025-10-28 | 2025-11-06 | Open | FPS drops to 30 during multi-enemy combat | Console dev kit | 5 | Optimization needed for console | 11 | Risk #2

## Notes
Key Highlights
→ This log captures key issues and bugs identified during the development of the 2D action-adventure game.
→ It is aligned with the Project Plan (task-level links) and Risk Register (early warnings and mitigations).
→ Follows best practices from game production:
▪ Severity classification: Blocker, Critical, Major, Minor.
▪ Priority levels: P1 (highest) to P4 (lowest).
▪ Owner column clarifies who is responsible for triage or resolution.
▪ Linked Task ID allows traceability to planned tasks (e.g. internal testing, optimization).
▪ Risk Link references if the issue confirms or mitigates a known risk (e.g. performance).
▪ SLA sets resolution targets to ensure timely delivery before milestones like the Vertical Slice.
▪ Environment helps identify which platform/build the bug affects (e.g. PC build 0.1, console dev kit).
→ Helps maintain quality, accountability, and steady progress toward Beta and Launch.