## RR
ID | Risk Statement | Category | Probability (1-5) | Impact (1-5) | Risk Score (P*I) | Owner | Mitigation Plan | Trigger / Early Warning | Status | Target Date
1 | Scope creep in vertical slice | Scope | 3 | 4 | 12 | Pedro (Producer) | Strict change control; freeze scope; define scope in GDD and lock post approval. | Requests to add new features after lock | Open | 2025-11-05
2 | Key asset delivery delay (art or level design) | Schedule | 2 | 4 | 8 | Ana (Art Director) | Add schedule buffer; prioritize key assets; parallelize work where possible. | Missed WIP reviews or key asset milestone | Open | 2025-11-03
3 | Performance issues on handheld console | Technical | 3 | 4 | 12 | Luis (Lead Programmer) | Test early on target hardware; optimize assets/code; reduce unnecessary effects. | FPS drops during Vertical Slice test | Open | 2025-10-30
4 | Gameplay or narrative not fun | Design | 2 | 5 | 10 | Carlos (Game Designer) | Internal playtests; feedback early (Vertical Slice); iterate before expanding content. | Negative feedback during internal reviews | Open | 2025-10-26
5 | Team coordination issues or resource gaps | Organizational | 2 | 3 | 6 | Pedro (Producer) | Weekly syncs; document design/code well; monitor workload; prepare for coverage. | Missed syncs or delivery inconsistencies | Open | 2025-10-15

## Notes
Key Highlights
→ This register identifies 5 realistic risks in the development of a 2D action-adventure indie game, covering scope, schedule, technical, design, and organizational dimensions.
→ Risks are evaluated using a 1–5 scale for probability and impact, resulting in a priority score (P×I).
→ Each risk is assigned a clear mitigation plan and an owner responsible for monitoring and responding.
→ Triggers or early warnings help detect when a risk might materialize (e.g., delays, negative feedback, FPS issues).
→ The register is aligned with the project plan's milestones and timing (e.g., scope creep linked to the Vertical Slice milestone).
→ This structure reflects common formats used in game studios (inspired by ClickUp, GameDeveloper.com) and shows proactive production thinking.